## Slide 1: Ad-Hoc Club Hub Committee Report
Vice-President (Clubs and Services)

## Slide 2: Club Hub Project
Purpose: Large scale revamp of the Clubs and Services Portfolio administration into an online club management portal called the Club Hub.
Phases: There are 6 major phases
  Phase 1: Research (complete)
  Phase 2: Design (complete)
  Phase 3: Consultation (complete)
  Phase 4: Development
  Phase 5: Implementation
  Phase 6: Assessment

## Slide 3: Phase 1: Research
Step 1: Identify problems with our current club structure
  Institutional memory
  Outdated constitutions
  Room bookings
  Club bank accounts
  Club Funding
  Club Auditing
  Club Offices/Lockers
  Club insurance
  Club elections
  Sponsorship and Contracts
  Interclub conflicts
  McGill/SSMU MoA
  PGSS/SSMU MoA
  High turnover/short lifespan
  Bad record-keeping
  Historical precedence

## Slide 4: Phase 1: Research
Step 2: Research similar structures at other universities
Read bylaws and policies for over 40 universities across Canada and the United States
Contacted and Skyped with 12 universities’ student association re: their club structures (shown to the right)
Ryerson University
Concordia University
University of Calgary
University of Ottawa
University of Toronto
York University
University of Lethbrudge
University of Manitoba
University of Waterloo
Simon Fraser University
University of British Columbia
Humber College

## Slide 5: Phase 1: Research
Attended UBC’s Student Union Development Summit and hosted a Clubs Portfolio Caucus
Together with other VP (CS) equivalents, we created the Clubhouse, a cross-campus sounding board for ideas and issues
Major takeaways:
  Our club structure is unique, however our problems are not
  Club administrative support is much higher at other universities
  Number of clubs positively correlates with the amount of resources provided

## Slide 6: Phase 2: Design
Major core features
  Robust
    Ideally, the system integrates different facets of club administration while simultaneously being flexible enough to adapt to an ever changing structure.
  User Friendly
    Ideally, the system is intuitive such that clubs can take ownership over administering themselves.
  Customizable
    Ideally, the system would be customized to tailor to each student and each club’s needs.

## Slide 7: Phase 2: Design
Major features:
  Robust - a module structure would allow for workflows to be automated independently while still allowing for interconnectedness. Modules could be commissioned over time and added to the Club Hub as new workflows emerge.
  User Friendly – a consolidation of all platforms clubs interact with (website, SSMURBS, Wufoo, etc) would allow for less confusion by reducing the bureaucracy generated through administrative work
  Customizable - integration with Shibollith, McGill’s student login software, would allow SSMU to customize the information that a student or club is able to access

## Slide 8: Phase 2: Design
1st layer (Yusuf’s dream)
  Public facing-website, contains information useful to prospective students, parents and teachers
2nd layer (Arthur’s dream)
  Student website, accessed through Shibollith, gives each student access to information relevant to them as a student such as a clubs listing, academic rights, SSMU services, etc

## Slide 9
3rd layer (Eamses’ dream)
  Club website, accessed through registered executive positions, gives each club a centralized location to access all SSMU resources, manage their finances, and track their membership list
4th layer (Limbo)
  SSMU admin website, the back end of the Club Hub would consist of an overview of the other layers allowing SSMU better management of its groups as well as generate useful statistics

## Slide 10: Phase 3: Consultation
In order to consult students on their experience within clubs, the Ad-Hoc Club Hub Committee was created to draft a Club Survey as well as analyze its results
The Club Survey, consisting of 50 questions, went live on March 9th and closed on March 31st.
The Executive Committee approved allocating 2000$, from inactive club bank accounts whose funds had been recovered into the Club Fund, towards incentivizing the survey. The Club Hub Committee decided on ten 200$ grants to be raffled off.
A total of 431 responses of which 280 were complete responses. This represents 142 unique clubs which consists of 61.21% of all Clubs.

## Slide 11: Phase 3: Consultation
Major highlights
  57.50% of clubs would support the creation of an online club management portal, 5.35% disagree
  38.22% of clubs agree that SSMU provides enough resources, 18.93% disagree
    Space and Funding cited as most requested resources
  Between 52% and 82% of Clubs would attend a funding application workshop or an event planning workshop if offered
  No significant agreement (~50% agree and disagree) regarding how easy to navigate the website, however strong agreement that the information available is useful and easy to read
  60.56% of Clubs agree that they compete with too many other groups at Activities Night and 72.11% of Clubs would table for more days if Activities Night was hosted longer

## Slide 12: Phase 3: Consultation
Next steps:
  Announce the winners of the Club Survey raffle
  Continue to analyze the data from the Club Survey and prepare a report of recommendations for future VP (CS)s
  Follow up with Clubs and Services that are part of the pilot project for myInvolvement

## Slide 13: Next year
Phase 4: Development
  A future VP (CS) will be responsible for sourcing quotes from software development companies and working towards the development of the Club Hub.
Phase 5: Implementation
  A future VP (CS) will be responsible for implementing the Club Hub into SSMU’s club administration.
Phase 6: Assessment
  A future VP (CS) will be responsible for assessing any logistical issues with the implementation